## Job Plan Tasks - 10_11_2024
Location | Task | Description | Duration | Station | Work Group | Comments
Andrews |  | CL-1) High Voltage Disconnect Verification | 2 | 1 | Chassis Line
Andrews |  | CL-2) Engine/ Drive Unit Assembly Removal & Installation | 90 | 1 | Chassis Line | Combined Hours: 40 + 50 = 90
Andrews |  | CL-3) Front Axle Removal & Installation | 40 | 1 | Chassis Line | Combined Hours: 16 + 24 = 40
Andrews |  | CL-4) Rear Axle Removal & Installation | 40 | 1 | Chassis Line | Combined Hours: 16 + 24 = 40
CTF |  | ES-1) CTF - Disassemble/ Reassemble Powerplant; Engine Tear Down/ Rebuild & Dyno; Drive Unit Tear Down/ Rebuild & Dyno | 162 | CTF | CTF Eng/Trans | Combined ES-1) with ES-2) & TS-1) 16 + 50 + 20 + 24 + 20 + 20 + 12 = 162 Hours
CTF |  | SU-1) CTF - Surge Tank Tear Down & Rebuild | 4 | CTF | CTF Surge Tank
CTF |  | AS-1) CTF - Front Axle Tear Down & Rebuild | 40 | CTF | CTF Eng/Trans
CTF |  | AS-2) CTF - Rear Axle/ Differential Tear Down & Rebuild | 40 | CTF | CTF Eng/Trans
CTF |  | MS-1) CTF - Machine Shop Inspection and Repair | 10 | CTF | Machine Shop
CTF |  | BP-1) CTF - Paint Engine | 2 | CTF | Body/ Paint
CTF |  | GS-1) CTF Graphics: Interior & Exterior Decals | 20 | CTF | Graphics
Andrews |  | P-1) Pneumatics | 32 | 1 | Small Units
Andrews |  | E-1) Bulkhead Electrical | 40 | 1 | Small Units
Andrews |  | E-2) Battery Compartment | 16 | 1 | Small Units
Andrews |  | E-3) Exterior Lighting Electrical repair | 16 | 1 | Small Units
Andrews |  | E-4) Interior Electrical | 36 | 1 | Small Units | Combined Hours: 16:00 + 20 = 36
Andrews |  | AC-1) HVAC System | 40 | 1 & 5 | HVAC
Andrews |  | FB-1) Fare Box Removal, Overhaul, & Installation | 10 | 1 & 5 | Farebox | Combined Hours: 9 + 1 = 10
Andrews |  | WC-1) Wheelchair Ramp Service | 16 | 1 & 5 | Chassis Line
Andrews |  | BS-1) Bus Interior/ Exterior Repairs | 120 | 2 | Body Shop | Combined Hours: 4 + 116 = 120
Andrews |  | PS- 1) Exterior/ Interior Preparations & Refinishing | 100 | 3 | Paint Shop
Andrews |  | BS-2) Interior/ Exterior Installations & Doors Operations | 160 | 4 | Body Shop
Andrews |  | CL-5) Final Inspection, Road Test Pre-Check, & Clean/ Release Bus | 40 | 5 | Chassis Line | Combined Hours: 32 + 8 = 40
1076